P R O J E C T   P L A N

SafeIQ Platform

20-Week Delivery Plan & Estimate (~5 Months)

Sprint-based delivery: discovery, parallel build tracks, QA, deploy

Agency:  SAARZ Int.

Prepared by:  Umair — Senior AI/ML Engineer

Dated:  July 8, 2026

SafeIQ — Development Requirements & Milestone Plan

Project: SafeIQ (AI-powered Employee Safety & Compliance Platform)

Date: July 2026   |   Version: 1.0   |   Prepared by: Umair

Contents

Project Overview3

Milestone 1 — Discovery & Architecture3

Milestone 2 — Authentication & Multi-Tenant Foundation4

Milestone 3 — Onboarding CMS4

Milestone 4 — Team Management5

Milestone 5 — AI Knowledge Base — RAG Engine5

Milestone 6 — AI Chat Agent (Floating Widget)6

Milestone 7 — Organisation Dashboard6

Milestone 8 — Communication Platform7

Milestone 9 — Mobile Apps (iOS & Android)7

Milestone 10 — Calendar & Scheduling8

Milestone 11 — AI Research Assistant8

Milestone 12 — Audit, Compliance & Security8

Milestone 13 — API Platform9

Milestone 14 — QA, UAT & Production Deployment9

Total Project Timeline Summary11

Questions & Concerns for Client12

Document Notes13

Project Overview

SafeIQ is a multi-tenant platform where an organisation loads its approved documents into a private knowledge base (RAG) and its employees ask an always-available AI agent that answers only from that approved content. Anything the agent cannot answer is escalated to the organisation. Every upload, change, question and answer is captured in an immutable audit trail so the organisation can prove which guidance an employee was given — the platform’s core value is risk management and legal evidence, not a general chatbot.

The same agent is the organisation’s communication hub (chat, voice, video, screen share, media) and is delivered on web and mobile. The platform also provides an onboarding video CMS, a team-management layer, an organisation dashboard, a calendar, an AI research assistant, audit / compliance, security and an open API.

Milestone 1 — Discovery & Architecture

Estimated Duration: ~1 Week     |     Dev Effort: AI Lead, Backend Lead, DevOps, UI/UX

Tasks

- Run requirement workshops to close every CRITICAL and HIGH-PRIORITY open item in the Questions & Concerns section, and produce a signed-off requirements addendum — the fixed price depends on this.

- Run technical spikes / proofs-of-concept on the highest-risk unknowns before the fixed estimate is committed: (a) RAG grounding — answer only from approved content, cite sources, refuse and escalate otherwise — on a real sample of client documents; (b) the floating-widget mechanism for the chosen delivery model (browser extension / desktop app / injected widget); (c) a real-time voice, video and screen-share round-trip; (d) mobile floating-widget and lock-screen-recording feasibility and legality (especially iOS).

- Produce Architecture Decision Records for the irreversible choices: LLM provider, vector database, tenant-isolation model, real-time stack and the audit-ledger technology.

- Produce the solution architecture and AWS design (London region), including the shared real-time backbone (WebSocket / WebRTC, TURN / SFU) used by chat, calls, screen share and the live feeds.

- Design the multi-tenant database schema and tenant-isolation strategy (organisations, employees, RAGs, documents, audit), including per-tenant vector-store namespace isolation.

- Design the AI / RAG architecture end to end — ingestion, chunking, embeddings, hybrid retrieval, re-ranking, grounding and escalation — including the AI-assisted content placement the PRD requires (drop content in and the AI files it correctly).

- Define the RAG evaluation strategy: a grounding / hallucination test harness, citation-accuracy measurement and refusal red-teaming, since the audit trail's evidential value depends on the agent never answering outside approved content.

- Produce the security and compliance design, and resolve the GDPR-erasure vs immutable-audit conflict (recommended: hash, version, timestamp and owner on a tamper-evident append-only ledger; PII and full documents held off-ledger and erasable).

- Produce a running-cost model at the client's confirmed scale (LLM per question, embeddings, vector DB, storage, real-time / TURN egress) so the fixed price is defensible.

- Write the API specification.

- Set up repositories, infrastructure-as-code (Terraform), the dev / staging / production environments, secrets management, CI/CD and AI cost / token observability.

- Refine the delivery plan into a dependency graph and critical path, and confirm the MVP vs phase-2 split (recommended: the safety / emergency module and any public-ledger work sit in phase 2 or behind a spike).

- Deliver the discovery pack (architecture, security, RAG design, cost model, refined plan) and obtain design sign-off before build begins.

Time Estimates

Time Estimates:  Requirement workshops & sign-off: 2 days | Technical spikes / PoCs (RAG grounding, widget, real-time, mobile): 3 days | Architecture, ADRs, DB & RAG design incl. evaluation strategy: 2 days | Security, compliance & GDPR / audit resolution, API spec: 1 day | Cost model & delivery-plan refinement: 1 day | Repo, IaC, environments & CI/CD: 1 day | Total: ~10 days (≈2 weeks)

Milestone 2 — Authentication & Multi-Tenant Foundation

Estimated Duration: ~3 days     |     Dev Effort: 2 Backend, 1 DevOps

User Workflow

Screen 1: Sign-up (Organisation or Employee) → Full Name, Email, Password

Screen 2: Email / OTP verification

Screen 3: Identity verification (KYC) — provider TBC with client

Screen 4: Employee join via magic link → auto-binds to the organisation

Screen 5: Account settings (country, language, roles)

Tasks

- Build organisation and employee registration and login

- Integrate KYC provider (Onfido / Jumio — TBC with client)

- Build magic-link invitations (email link and shareable link)

- Implement roles and permissions

- Build the multi-tenant data model with database-level tenant isolation

- Build account settings and per-user country / language

- Lay the audit-log foundation used across all modules

Time Estimates

Time Estimates:  Registration & login:  day 1 | KYC integration:  day 1 | Magic links & roles:  day 2  | Multi-tenant isolation:  day 2  | Settings & audit base: day 3 | Total: ~3 days

Milestone 3 — Onboarding CMS

Estimated Duration: ~1 Week     |

User Workflow

Screen 1: Onboarding page — 3 videos across, 9 per page; AI search bar; end-user-type dropdown

Screen 2: Hover a thumbnail → description; click → open to read and watch

Screen 3: Share a video by email or to a registered user

Tasks

- Build the video CMS (upload media, thumbnail, title, description)

- Control video order from the CRM (operator side)

- Build search and filtering (by end-user type, view all)

- Build AI-assisted search (“describe what you want support with”)

- Build hover-description and click-to-view behaviour

- Build share by email / to a registered user

- Add onboarding analytics

Time Estimates

Time Estimates:  Video CMS & upload: 2 days  | Search & filtering & AI search: 1 day | Share & analytics   UI polish: 2 days | Total: ~5 days

Milestone 4 — Team Management

Estimated Duration: ~2 Weeks     |     Dev Effort: 1 Backend, 1 Frontend

User Workflow

Screen 1: Team → invite new person (email or shareable magic link) or view members

Screen 2: Invite log — resend or cancel

Screen 3: Member profile → details, notes, alerts, assigned RAGs + access codes, activity

Tasks

- Build invite by email and by shareable magic link

- Build accept-invite flow that binds the member to the organisation

- Build the invite log (logged, resendable, cancellable)

- Build member profiles (details, notes, alerts)

- Build RAG assignments with a unique access code per member

- Build per-member activity view inside each assigned RAG

- Build assignment management

Time Estimates

Time Estimates:  Invite / accept flow: 3 days | Profiles, notes & alerts: 2 days | Assignments & access codes: 2 days | Activity views: 2 days | UI polish: 1 day | Total: ~10 days

Milestone 5 — AI Knowledge Base — RAG Engine (Core Module)

Estimated Duration: ~3.5 Weeks     |     Dev Effort: 2 AI Engineers, 1 Backend

User Workflow

Employee asks → search organisation documents → find approved content → answer only from that content, with citations

If the answer is not in the content → refuse and escalate the question to the organisation

Tasks

- Build document upload (PDF, Word, TXT, Markdown, images via OCR, video metadata)

- Build the processing pipeline (OCR, cleaning, chunking, metadata extraction)

- Generate embeddings (model TBC) and store vectors (pgvector — TBC with client)

- Build hybrid retrieval (vector + metadata) with re-ranking

- Build strictly grounded answering with source citation, prompt templates and conversation memory

- Build RAG management (version history, update, delete, re-index)

- Build user assignment and per-RAG analytics

- Build escalation of unanswerable questions to the organisation

- Build a grounding / hallucination evaluation harness with a labelled test set and a regression gate on citation accuracy and refusal behaviour.

- Red-team the refusal path so the agent never answers outside approved content, and measure grounding on a held-out set before each release.

Time Estimates

Time Estimates:  Upload & processing & Embeddings & vector storage: 5 days | Retrieval & re-ranking & Grounded answers & citations: 5  days | RAG management & Assignment & analytics: 5 days | Grounding evaluation, citation accuracy & refusal red-teaming: 3 days | Total: ~18 days

Milestone 6 — AI Chat Agent (Floating Widget)

Estimated Duration: ~3 Weeks     |     Dev Effort: 1 AI Engineer, 1 Frontend

User Workflow

Screen 1: Agent docked bottom-right; floats where the platform allows (behaviour TBC — see Questions)

Screen 2: Employee enters an access code → switches to the assigned RAG

Screen 3: Employee asks → streamed answer from the active RAG; organisation / other-user messages also arrive here

Tasks

- Build the floating widget and chat UI with streaming responses

- Build conversation history and message search

- Build access-code entry and RAG switching

- Build audio input (speech-to-text) and text-to-speech

- Route organisation and other-user messages through the agent

Time Estimates

Time Estimates:  Widget & chat UI: 3 days | Streaming & history: 2 days | Access codes & RAG switching: 3 days | Voice (STT/TTS): 3 days | Search & integration: 2 days | Total: ~15 days

Milestone 7 — Organisation Dashboard

Estimated Duration: ~1 Week     |     Dev Effort: 1 Frontend, 1 Backend

Tasks

- Build the live questions feed across all RAGs

- Build the alerts feed and alert-category rules

- Build the pending / unanswered questions queue

- Build analytics and reports

- Build the employee activities view

- Build urgent routing to designated members

Time Estimates

Time Estimates:  Live feed & alerts: 2 days | Pending queue & routing: 1 day | Analytics & reports: 1 day | Activities & UI: 1 day | Total: ~5 days

Milestone 8 — Communication Platform

Estimated Duration: ~3 Weeks     |     Dev Effort: 2 Backend, 1 Frontend

User Workflow

Employee → 1:1 chat via the agent → voice / video call → screen share → media

Organisation controls who each employee may communicate with (permission lists shown in the agent)

Tasks

- Build 1:1 chat via the agent with presence and typing

- Build permission lists (who can talk to whom)

- Build voice and video calls

- Build screen sharing (WebRTC / Twilio — TBC with client)

- Build media sharing

- Build push notifications (Firebase + AWS SNS — TBC)

Time Estimates

Time Estimates:  Chat & presence: 3 days | Voice / video calls: 4 days | Screen share: 3 days | Media & permissions: 3 days | Push: 2 days | Total: ~15 days

Milestone 9 — Mobile Apps (iOS & Android)

Estimated Duration: ~3 Weeks     |     Dev Effort: 2 Mobile Engineers

Tasks

- Build the Android and iOS apps (Flutter — TBC with client)

- Build authentication

- Build the agent chat, media and voice

- Build push notifications

- Implement the floating widget where the platform permits (behaviour TBC — see Questions)

- Prepare App Store and Google Play submissions

Time Estimates

Time Estimates:  App scaffolding & auth: 3 days | Chat & media: 4 days | Voice: 2 days | Push: 2 days | Widget behaviour: 2 days | Store prep: 2 days | Total: ~15 days

Milestone 10 — Calendar & Scheduling

Estimated Duration: ~1.5 Weeks     |     Dev Effort: 1 Backend, 1 Frontend

Tasks

- Build booking and events

- Build activities attached to bookings

- Attach RAG name and access code to a booking

- Build notifications and reminders

Time Estimates

Time Estimates:  Booking & events: 3 days | Activities & RAG assignment: 2 days | Notifications: 2 days | Total: ~7 days

Milestone 11 — AI Research Assistant

Estimated Duration: ~2 Weeks     |     Dev Effort: 1 AI Engineer, 1 Backend

User Workflow

Organisation asks (e.g. “Find the latest UK Health & Safety law”) → AI searches → summarises → suggests → organisation approves → imported into the RAG

Tasks

- Build the organisation research query

- Build AI search (internal knowledge vs public internet — TBC with client)

- Build summarise and suggest

- Build the human approval step

- Import approved content into the RAG

Time Estimates

Time Estimates:  Research query & search: 3 days | Summarise & suggest: 3 days | Approve & import: 3 days | UI: 1 day | Total: ~10 days

Milestone 12 — Audit, Compliance & Security

Estimated Duration: ~3 Weeks     |     Dev Effort: 1 Backend, 1 DevOps

Tasks

- Build document and RAG versioning

- Build a tamper-evident, immutable audit trail (only hash + version + timestamp + owner on-chain; full documents off-chain — ledger technology TBC, see Questions)

- Build document history and usage history

- Build GDPR export and erasure workflows

- Build 2FA and encryption at rest and in transit

- Build IP lock, session management and access logs

- Build rate limiting

Time Estimates

Time Estimates:  Audit trail & versioning: 4 days | Immutable ledger: 3 days | GDPR export/erasure: 2 days | 2FA & encryption: 3 days | IP lock & sessions: 2 days | Rate limiting: 1 day | Total: ~15 days

Milestone 13 — API Platform

Estimated Duration: ~2 Weeks     |     Dev Effort: 1 Backend

Tasks

- Build the REST API

- Build authentication and API keys

- Build webhooks

- Build rate limits

- Build Swagger / OpenAPI documentation

Time Estimates

Time Estimates:  REST endpoints: 4 days | Auth & keys: 2 days | Webhooks: 2 days | Rate limits & docs: 2 days | Total: ~10 days

Milestone 14 — QA, UAT & Production Deployment

Estimated Duration: ~3 Weeks     |     Dev Effort: 2 QA, 1 DevOps

Tasks

- Functional testing of all flows (register, RAG, agent, dashboard, comms, mobile)

- Security testing

- Performance and load testing

- Regression testing

- UAT with the client

- AWS production setup, CI/CD and scaling

- Monitoring (CloudWatch), backup, logging and documentation, then go-live

Time Estimates

Time Estimates:  Functional & security testing: 4 days | Performance & load: 3 days | Regression & UAT: 3 days | Production setup & CI/CD: 3 days | Monitoring, backup & go-live: 2 days | Total: ~15 days

Total Project Timeline Summary

| Milestone | Module | Duration |
| --- | --- | --- |
| Milestone 1 | Discovery & Architecture | ~2 Weeks |
| Milestone 2 | Authentication & Multi-Tenant Foundation | ~3 days |
| Milestone 3 | Onboarding CMS | ~1 Week |
| Milestone 4 | Team Management | ~2 Weeks |
| Milestone 5 | AI Knowledge Base — RAG Engine (Core Module) | ~3.5 Weeks |
| Milestone 6 | AI Chat Agent (Floating Widget) | ~3 Weeks |
| Milestone 7 | Organisation Dashboard | ~1 Week |
| Milestone 8 | Communication Platform | ~3 Weeks |
| Milestone 9 | Mobile Apps (iOS & Android) | ~3 Weeks |
| Milestone 10 | Calendar & Scheduling | ~1.5 Weeks |
| Milestone 11 | AI Research Assistant | ~2 Weeks |
| Milestone 12 | Audit, Compliance & Security | ~3 Weeks |
| Milestone 13 | API Platform | ~2 Weeks |
| Milestone 14 | QA, UAT & Production Deployment | ~3 Weeks |

SEQUENTIAL EFFORT: ~31 weeks. DELIVERY WITH A 12-PERSON TEAM RUNNING PARALLEL TRACKS: ~20 weeks (~5 months), contingent on the CRITICAL answers and the discovery spikes landing.

How the timeline compresses: Milestones 1–2 (foundation) run first and everything depends on them. After that the team splits into parallel tracks — an AI track (RAG → Chat Agent → Research), a web/backend track (Onboarding → Team → Dashboard → Calendar → API), and a comms/mobile track (Communication → Mobile) — with Audit/Compliance/Security woven across them. QA, UAT and production deployment close the plan. The critical path (foundation → RAG → Chat Agent → mobile/integration → QA/deploy) is what sets the ~20-week delivery.

Note: timelines assume the CRITICAL questions below are answered before Milestone 1 and that design sign-off precedes each milestone.

Questions & Concerns for Client

The PRD contains more than 40 unclear requirements. The items below must be answered to scope and price accurately. Items marked CRITICAL are blockers. For estimation, one option per open item was assumed and is flagged inline as “TBC” in the milestones above.

CRITICAL — Must Answer before Development Starts

- Which LLM? GPT, Claude, Gemini, Llama, Mistral or self-hosted? This is the single biggest cost driver — per-question price varies by an order of magnitude and sets the whole running-cost model.

- Expected number of users? 10, 100 or 10,000 per organisation, and how many organisations? The architecture and infrastructure cost change completely with scale.

- Expected document volume? 10 MB, 100 GB or 1 TB per organisation? This drives storage, indexing and vector-database cost.

- Blockchain / audit trail? Confirm that only the hash, version, timestamp and owner go on-chain (full documents cannot). Which ledger technology is expected?

- Safety / emergency features? The PRD lists a siren, safe-word detection, police alerts and lock-screen recording. These depend on unresolved items below (police integration, always-listening on mobile) and are EXCLUDED from this estimate until confirmed. Please confirm scope and intended behaviour.

HIGH PRIORITY — Need Answers Before Milestone Design

- Floating widget (web/desktop)? Browser extension, injected JavaScript widget, desktop / Electron app, or a Windows overlay? Each is a very different build.

- Mobile floating widget? A true always-on-top overlay is restricted on iOS and limited on Android. Please confirm the intended behaviour per platform.

- Audio safety detection? Always-listening or user-triggered? Background recording? This hits mobile OS restrictions (especially iOS) and privacy / GDPR duties.

- Police integration? How? There is no general UK 999 API for automated dispatch. Please confirm the intended escalation mechanism.

- AI research scope? Should the research assistant search the public internet or only internal / approved sources?

- Screen sharing / video? WebRTC (self-hosted), Twilio, Daily or Zoom SDK? Different cost and effort.

- Vector database? pgvector (assumed) versus Pinecone, Qdrant, Milvus or OpenSearch?

LOWER PRIORITY — Confirm Before Final Sign-Off

- RAGs per organisation? Is there a cap — 100, 1,000 or unlimited? Storage pricing depends on it.

- Real-time backup? AWS Backup, cross-region, S3 versioning or database replication? Please confirm the expected recovery objectives.

- Languages at launch? Which languages, and is right-to-left support needed? Each user can set their own country and language.

- KYC scope? Which provider (assumed managed provider — TBC), and does full KYC apply to employees or only to organisation owners?

Document Notes

This plan was prepared from the client PRD. More than 40 unclear requirements were identified; for pricing, one reasonable option per open item was assumed and is flagged as TBC in the milestones and listed under Questions & Concerns. The safety / emergency module is excluded pending clarification of the police-integration and always-listening red flags.

Next Steps: (1) Client reviews this plan; (2) client answers all CRITICAL and HIGH PRIORITY questions; (3) design sign-off per milestone; (4) a fixed cost estimate is issued once the three CRITICAL pricing items are confirmed; (5) development begins at Milestone 1.